## Data
Department | Team | Project | Epic | Task | Days
Development | React | Soda shop | Rewrite | BR-343 | 0.5
Development | React | Soda shop | Rewrite | BR-346 | 3.5
Development | React | Soda shop | Rewrite | BR-349 | 15
Development | React | Soda shop | Rewrite | BR-423 | 0.5
Development | React | Soda shop | Rewrite | BR-443 | 35
Development | React | Soda shop | Rewrite | BR-466 | 120
Development | React | Soda shop | Rewrite | BR-481 | 0
Development | React | Soda shop | Rewrite | BR-482 | 60
Development | React | Soda shop | New product search | BR-245 | 6
Development | React | Soda shop | New product search | BR-301 | 12
Development | React | Soda shop | New product search | BR-302 | 1
Development | React | Soda shop | New product search | BR-305 | 4
Development | Java | McShop | Analysis | BR-543 | 4.5
Development | Java | McShop | Analysis | BR-546 | 4
Development | Java | McShop | Analysis | BR-549 | 2
Development | Java | McShop | Analysis | BR-623 | 1
Development | Java | McShop | Analysis | BR-644 | 8
Development | Java | McShop | Analysis | BR-666 | 15
Development | Java | McShop | Analysis | BR-681 | 80
Development | Java | McShop | Analysis | BR-682 | 300
Development | Java | McShop | Reports | BR-745 | 30
Development | Java | McShop | Reports | BR-702 | 20
Development | Java | McShop | Reports | BR-705 | 10
Development | Java | McShop | Performance | BR-746 | 300
Development | Java | McShop | Performance | BR-762 | 20
Development | Java | DoD | GUI | DOD-003 | 4.5
Development | Java | DoD | GUI | DOD-007 | 60
Development | Java | DoD | Encryption | DOD-022 | 30
Development | Java | DoD | Mining | DOD-033 | 110
Development | Java | DoD | Mining | DOD-034 | 80
Sales | Philippines | New leads | Initial contact | SL-231 | 4
Sales | Philippines | New leads | Initial contact | SL-232 | 6
Sales | Philippines | New leads | Initial contact | SL-233 | 10
Sales | Philippines | New leads | Initial contact | SL-234 | 1
Sales | Philippines | New leads | Initial contact | SL-236 | 1.5
Sales | Philippines | New leads | Initial contact | SL-300 | 4
Sales | Philippines | New leads | Demo | SL-126 | 1
Sales | Philippines | New leads | Demo | SL-222 | 4
Sales | Government | Bitcoin | Bitcoin | GV-003 | 10
Sales | Government | Bitcoin | Bitcoin | GV-006 | 20
Sales | Government | Bitcoin | Bitcoin | GV-010 | 50
Sales | Government | Etherum | Etherum | GV-101 | 10
Quality assurance | QA | Releases | v2.9.2 | QA-113 | 0.5
Quality assurance | QA | Releases | v2.9.2 | QA-114 | 1.5
Quality assurance | QA | Releases | v2.9.2 | QA-115 | 1
Quality assurance | QA | Releases | v2.9.2 | QA-116 | 1
Quality assurance | QA | Releases | v2.9.2 | QA-117 | 1.5
Quality assurance | QA | Releases | v2.9.2 | QA-118 | 2
Quality assurance | QA | Releases | v2.9.2 | QA-119 | 3
Quality assurance | QA | Releases | v2.9.2 | QA-120 | 1
Quality assurance | QA | Releases | v2.9.2 | QA-121 | 2
Quality assurance | QA | Releases | v2.9.2 | QA-122 | 1
Quality assurance | QA | Releases | v2.9.2 | QA-123 | 1.5
Quality assurance | QA | Releases | v2.9.2 | QA-124 | 7
Quality assurance | QA | Releases | v2.9.3 | QA-211 | 5
Quality assurance | QA | Releases | v2.9.3 | QA-222 | 50
Quality assurance | QA | Hotfixes | Bugs | QA-131 | 2
Quality assurance | QA | Hotfixes | Bugs | QA-132 | 1
Quality assurance | QA | Hotfixes | Bugs | QA-133 | 0.25
Quality assurance | QA | Hotfixes | Bugs | QA-134 | 1
Quality assurance | QA | Hotfixes | Bugs | QA-135 | 2
Quality assurance | QA | Hotfixes | Bugs | QA-136 | 1
Quality assurance | QA | Hotfixes | Bugs | QA-137 | 0.5
Quality assurance | QA | Hotfixes | Bugs | QA-139 | 1
Quality assurance | QA | Hotfixes | Bugs | QA-140 | 3

## DEV
Development
Head | Michael
React |  |  | Lead: John
Project | Epic | Duration | Task | Estimate | Spent | Epic health | Project health
Soda shop | Rewrite | 234.5 | BR-343 | 2 | 0.5 | 183.2% | 170.5%
|  |  | BR-346 | 7 | 3.5
|  |  | BR-349 | 12 | 15
|  |  | BR-423 | 1 | 0.5
|  |  | BR-443 | 20 | 35
|  |  | BR-466 | 70 | 120
|  |  | BR-481 | 6 | 0
|  |  | BR-482 | 10 | 60
| New product search | 23 | BR-245 | 6 | 6 | 100%
|  |  | BR-301 | 10 | 12
|  |  | BR-302 | 2 | 1
|  |  | BR-305 | 5 | 4
Total mandays |  | 257.5
Java |  |  | Lead: Mary
Project | Epic | Duration | Task | Estimate | Spent | Epic health | Project health
McShop | Analysis | 414.5 | BR-543 | 4 | 4.5 | 206.2% | 112.3%
|  |  | BR-546 | 4 | 4
|  |  | BR-549 | 2 | 2
|  |  | BR-623 | 1 | 1
|  |  | BR-644 | 10 | 8
|  |  | BR-666 | 20 | 15
|  |  | BR-681 | 60 | 80
|  |  | BR-682 | 100 | 300
| Reports | 60 | BR-745 | 25 | 30 | 41.38%
|  |  | BR-702 | 100 | 20
|  |  | BR-705 | 20 | 10
| Performance | 320 | BR-746 | 200 | 300 | 106.7%
|  |  | BR-762 | 100 | 20
DoD | GUI | 64.5 | DOD-003 | 40 | 4.5 | 71.67%
|  |  | DOD-007 | 50 | 60
| Encryption | 30 | DOD-022 | 25 | 30 | 120%
| Mining | 190 | DOD-033 | 100 | 110 | 95%
|  |  | DOD-034 | 100 | 80
Total mandays |  | 1079

## SALE
Sales
Head | Eric
Philippines |  |  | Lead: Marc
Project | Epic | Duration | Task | Estimate | Spent | Epic health | Project health
New leads | Initial contact | 26.5 | SL-231 | 6 | 4 | 110.4% | 116.7%
|  |  | SL-232 | 3 | 6
|  |  | SL-233 | 8 | 10
|  |  | SL-234 | 1 | 1
|  |  | SL-236 | 2 | 1.5
|  |  | SL-300 | 4 | 4
| Demo | 5 | SL-126 | 1 | 1 | 166.7%
|  |  | SL-222 | 2 | 4
Total mandays |  | 31.5
Government |  |  | Lead: Naomi
Project | Epic | Duration | Task | Estimate | Spent | Epic health | Project health
Bitcoin | Bitcoin | 80 | GV-003 | 5 | 10 | 320% | 200%
|  |  | GV-006 | 10 | 20
|  |  | GV-010 | 10 | 50
Etherum | Etherum | 10 | GV-101 | 20 | 10 | 50%
Total mandays |  | 90

## QA
Quality assurance
Head | Mickey
QA |  |  | Lead: Mickey
Project | Epic | Duration | Task | Estimate | Spent | Epic health | Project health
Releases | v2.9.2 | 23 | QA-113 | 0.5 | 0.5 | 95.83% | 135%
|  |  | QA-114 | 1 | 1.5
|  |  | QA-115 | 0.5 | 1
|  |  | QA-116 | 2 | 1
|  |  | QA-117 | 2 | 1.5
|  |  | QA-118 | 2 | 2
|  |  | QA-119 | 1 | 3
|  |  | QA-120 | 3 | 1
|  |  | QA-121 | 4 | 2
|  |  | QA-122 | 1 | 1
|  |  | QA-123 | 2 | 1.5
|  |  | QA-124 | 5 | 7
| v2.9.3 | 55 | QA-211 | 10 | 5 | 183.3%
|  |  | QA-222 | 20 | 50
Hotfixes | Bugs | 11.75 | QA-131 | 2 | 2 | 94%
|  |  | QA-132 | 0.5 | 1
|  |  | QA-133 | 0.5 | 0.25
|  |  | QA-134 | 1 | 1
|  |  | QA-135 | 2 | 2
|  |  | QA-136 | 0.5 | 1
|  |  | QA-137 | 1 | 0.5
|  |  | QA-139 | 3 | 1
|  |  | QA-140 | 2 | 3
Total mandays |  | 89.75

## Summary
Sweat shop ltd.
Row Labels | Sum of Days
Development | 1336.5
React | 257.5
Java | 1079
Sales | 121.5
Philippines | 31.5
Government | 90
Quality assurance | 89.75
QA | 89.75
Grand Total | 1547.75